## Sheet1
Project Number | Team 25
Project Name | Redesigning Intranet
Project Mentor | Yash Adivarekar
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Estimation error | Estimation error estimation
Week 1 (January 18 - January 24)
Preparing questions for the client meeting | Preparation | Vanshika, Shravani | 1 | 1 | Done | 0 | 0
Jotting down a detailed MoM | Documentation | Aviral | 1 | 1 | Done | 0 | 0
Github repository setup | Preparation | Nilanjana | 0.5 | 0.5 | Done | 0 | 0
Team meeting | Coordination, Preparation | Siddharth | 1 | 1 | Done | 0 | 0
Status Tracker | Documentation | Nilanjana | 0.5 | 0.5 | Done | 0 | 0
Week 2 (January 25 - January 31)
Preparing questions for the meeting | Preparation | Aviral | 0.5 | 0.5 | Done | 0 | 0
Jotting down a detailed MoM | Documentation | Shravani | 1 | 0.5 | Done | 0.5 | 100
Status tracker | Documentation | Nilanjana | 0.5 | 0.5 | Done | 0 | 0
Project synopsis | Documentation | Siddharth | 2 | 2 | Done | 0 | 0
Client meet | Coordination | Siddharth | 0.5 | 0.25 | Done | 0.25 | 100
Project plan | Documentation | Shravani | 2 | 0.5 | Done | 1.5 | 300
Week 3 (February 01 - February 08)
Status tracker | Documentation | Siddharth | 0.5 | 0.5 | Done | 0 | 0
Client meet | Coordination | Vanshika | 0.5 | 0.5 | Done | 0 | 0
Design template searching | Research | Aviral | 1.5 | 1 | Done | 0.5 | 100
Design shortlisting | Coordination | Nilanjana | 1.5 | 1 | Done | 0.5 | 100
Role Assignment | Coordination | Shravani | 1 | 1 | Done | 0 | 0