## Sheet1
Project Number | Team 25
Project Name | Redesigning Intranet
Project Mentor | Yash Adivarekar
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Estimation error | Estimation error estimation
Week 1 (January 18 - January 24)
Preparing questions for the client meeting | Preparation | Vanshika, Shravani | 1 | 1 | Done | 0 | 0
Jotting down a detailed MoM | Documentation | Aviral | 1 | 1 | Done | 0 | 0
Github repository setup | Preparation | Nilanjana | 0.5 | 0.5 | Done | 0 | 0
Team meeting | Coordination, Preparation | Siddharth | 1 | 1 | Done | 0 | 0
Status Tracker | Documentation | Nilanjana | 0.5 | 0.5 | Done | 0 | 0
Week 2 (January 25 - January 31)
Preparing questions for the meeting | Preparation | Aviral | 0.5 | 0.5 | Done | 0 | 0
Jotting down a detailed MoM | Documentation | Shravani | 1 | 0.5 | Done | 0.5 | 100
Status tracker | Documentation | Nilanjana | 0.5 | 0.5 | Done | 0 | 0
Project synopsis | Documentation | Siddharth | 2 | 2 | Done | 0 | 0
Client meet | Coordination | Siddharth | 0.5 | 0.25 | Done | 0.25 | 100
Project plan | Documentation | Shravani | 2 | 0.5 | Done | 1.5 | 300
Week 3 (February 01 - February 08)
Status tracker | Documentation | Siddharth | 0.5 | 0.5 | Done | 0 | 0
Client meet | Coordination | Vanshika | 0.5 | 0.5 | Done | 0 | 0
Design template searching | Research | Aviral | 1.5 | 1 | Done | 0.5 | 100
Design shortlisting | Coordination | Nilanjana | 1.5 | 1 | Done | 0.5 | 100
Role Assignment | Coordination | Shravani | 1 | 1 | Done | 0 | 0
Week 4 (February 09 - February 16)
Client meet | Coordination | Shravani | 0.5 | 0.5 | Done | 0 | 0
Jotting down a detailed MoM | Documentation | Aviral | 0.5 | 0.5 | Done | 0 | 0
Status tracker | Documentation | Siddharth | 0.5 | 0.5 | Done | 0 | 0
Software Requirement Specification Docs | Documentation | Nilanjana, Aviral, Siddharth | 3 | 2 | Done | 1 | 200
Week 5 (February 17 - February 24)
Status tracker | Documentation | Shravani | 0.5 | 0.5 | Done | 0 | 0
Client meet | Coordination | Nilanjana | 0.5 | 0.5 | Done | 0 | 0
Design template | Interfaces | Vanshika | 2 | 3 | Done | 1 | 100
Design Document | Preparation, Documentation | Aviral, Siddarth | 2 | 2 | Done | 0 | 0
Week 6 (February 24 - March 3)
Status tracker | Documentation | Shravani | 0.5 | 0.5 | Done | 0 | 0
Home Page design | Interfaces | Nilanjana | 2 | 3 | Done | 1 | 100
Office Page design | Interfaces | Aviral | 2 | 3 | Done | 1 | 100
Files Page design | Interfaces | Siddarth | 2 | 3 | Done | 1 | 100
View doc Page design | Interfaces | Vanshika | 2 | 3 | Done | 1 | 100
Edit doc Page design | Interfaces | Shravani | 2 | 3 | Done | 1 | 100
Week 7 (March 3 - March 10)
Status tracker | Documentation | Siddharth | 0.5 | 0.5 | Done | 0 | 0
Jotting down a detailed MoM | Documentation | Shravani | 0.5 | 0.5 | Done | 0 | 0
Final design layout | Interfaces | Team | 1 | 2 | Done | 1.5 | 300
Home Page design changes | Interfaces | Siddarth | 1.5 | 3 | Done | 1.5 | 300
Office Page design changes | Interfaces | Aviral | 1.5 | 3 | Done | 1.5 | 300
Archive Page design | Interfaces | Nilanjana | 1.5 | 3 | Done | 1.5 | 300
Contacts Page design | Interfaces | Vanshika | 1.5 | 3 | Done | 1.5 | 300
Pending Approval Page design | Interfaces | Shravani | 1.5 | 3 | Done | 1.5 | 300
Week 8 (March 11 - March 18)
Status tracker | Documentation | Siddharth | 0.5 | 0.5 | Done | 0 | 0
Jotting down a detailed MoM | Documentation | Shravani | 0.5 | 0.5 | Done | 0 | 0
Search/Archive Page Implementation | Interfaces | Shravani | 3 | 4 | Done | 1 | 200
User + Admin Home Page Implementation | Interfaces | Aviral | 5 | 5.5 | Done | 0.5 | 100
User + Admin Office Page Implementation | Interfaces | Siddharth | 5 | 6 | Done | 1 | 200
View File Page Implementation | Interfaces | Nilanjana | 3 | 3 | Done | 0 | 0
Contacts Page Implementation | Interfaces | Nilanjana, Vanshika | 3 | 3 | Done | 0 | 0
Pending Approval Page Implementation | Interfaces | Shravani | 3 | 3 | Done | 0 | 0
Presentation PPT | Documentation, Preparation | Vanshika, Shravani | 2.5 | 3.5 | Done | 1 | 200
All Page integration | Interfaces | Nilanjana, Aviral | 5 | 6 | Done | 1 | 200